## Week1
Project Title: Milestone 3 Release #: 0.2 Sprint #: 3
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a dev I would like to use SpringBeans, Spring Core and DI | Refactor Login module to use SpringBeans, Spring Core, and the DI | Sam | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 2 | As a dev I would like to use SpringBeans, Spring Core and DI | Refactor Registration module to use SpringBeans, Spring Core, and the DI | Calista | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 3 | As a user I would like to create new posts in my account | Post creation under myprofile page created using spring mvc | Casey | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 4 | As a dev I need a model class for posts | Post object model | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 5 | As a dev I need to have users posts stored in the database | Post Database functionality | Adam | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 10 | As a dev I need to be able to recreate my database and the data stored in it with a simple SQL command | Update DDL Scripts | Nick | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| 11 | As a dev I would like to have Sprints, burndown chart, and repo setup for project management. | Design and planning documentation | Tim | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | As a dev I would like the design of the site to be updated | Css updates, navigational menu, and applicationConfiguration updates | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 8 | 6.8571 | 5.7143 | 4.5714 | 3.4286 | 2.2857 | 1.1429 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 7 | 6 | 6 | 6 | 6 | 5 | 0 | 0

## Week2
Project Title: Milestone 2 Release #: 0.1 Sprint #: Spring MVC
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 |  | Main Application Module: menu |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Main Application Module: style |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: active registration |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: Database |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database authentication |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: Principle object model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0