## Week1
Project Title: Milestone 5 Release #: 0.4 Sprint #: 5
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a dev I would like to have Maven Pom file | Add pom file | Casey | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 2 | As a dev I would like to have a database connected and working | Working database | Nick | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 3 | As a dev I would like to have all links working | Navigational links to each page working (updates to blogController) | Calista | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 4 | As a dev I need to have an about page | about.jsp added | Adam | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 5 | As a dev I need to have a good login page design | Design updates for Login page to match UI design | Tim | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 6 | As a dev I need to have a good postFeed design | Design updates for postFeed.jsp | Tim | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| 7 | As a dev I need to have a good newPost page design | Design updates for newPost.jsp | Sam | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 8 | As a user I would like to manage my account info and create new posts and edit old posts | myAccount.JSP page added | Tim | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| 9 | As a dev I would like to have Sprints, burndown chart, and repo setup for project management. | Design and planning documentation | Tim | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 9 | 7.7143 | 6.4286 | 5.1429 | 3.8571 | 2.5714 | 1.2857 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 9 | 9 | 8 | 8 | 7 | 5 | 0 | 0

## Week2
Project Title: Milestone 2 Release #: 0.1 Sprint #: Spring MVC
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 |  | Main Application Module: menu |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Main Application Module: style |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: active registration |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: Database |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database authentication |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: Principle object model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0