## Week1
Project Title: Milestone 6 Release #: 0.5 Sprint #: 6
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a dev I would like to utilize JQuery | Add a JQuery element to the website. | Calista | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2 | As a dev I would like to have a database connected and working | Working database | Nick | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 3 | As a dev I would like to have a page for viewing a single post after selecting one from the post feed | viewPost.jsp page added to website. | Sam | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 4 | As a dev I need users to be able to login and stay logged while navigating the website. | @session created for user | Adam | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 7 | As a dev I would like users to be able to make new posts and then store them | newPost form adds a post to the <Post> list | Casey | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 8 | As a dev I would like to have a well designed new post creation page | newPost.jsp UI design updates | Tim | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 9 | As a user I would like to have a well designed account manager page | myAccount.JSP UI design updates | Tim | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 10 | As a dev I would like to have Sprints, burndown chart, and repo setup for project management. | Design and planning documentation | Tim | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 8 | 6.8571 | 5.7143 | 4.5714 | 3.4286 | 2.2857 | 1.1429 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 8 | 8 | 7 | 7 | 5 | 5 | 0 | 0

## Week2
Project Title: Milestone 2 Release #: 0.1 Sprint #: Spring MVC
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 |  | Main Application Module: menu |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Main Application Module: style |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: active registration |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: Database |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database authentication |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: Principle object model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0