## Week1
Project Title: Milestone 2 Release #: 0.1 Sprint #: 2
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a user I would like to have a good idea of what I can do when I first visit this website | index.xhtml page designed for displaying basic functionality | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 2 | As a user I would like to register an account with this blog | register.xhtml page design and functional | Calista | 1 | [5 empty] | 0 | 2
| 3 | As a user I would like to login to the blog site | login.xhtml page designed and functioning | Casey | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 4 | As a user, once I am logged in I would like to be taken to the post feed | postFeed.xhtml page designed for initial login rerouting | Sam | 1
| 5 | As a dev I would like to verify user data | User authentification business logic | Casey | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 6 | As a dev I need a class that supports a user | User class | Tim | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | As a dev I need to be able to communicate with the database in order to complete all CRUD capabilties to a User | user database business model | Adam | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | As a dev I need a database where all user data is stored | MySQL or derby database setup | Nick | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | As a dev I would like to see at quick glance how my models are interacting with the database and each other | ER Diagram | Tim | 1 | 0 | 0 | 1 | 0 | 0 |  | 0
| 10 | As a dev I need to be able to recreate my database and the data stored in it with a simple SQL command | DDL Scripts | Nick | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | As a dev I would like to have Sprints, burndown chart, and repo setup for project management. | Design and planning documentation | Tim | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 11 | 9.4286 | 7.8571 | 6.2857 | 4.7143 | 3.1429 | 1.5714 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 11 | 10 | 9 | 8 | 8 | 8 | 0 | 0

## Week2
Project Title: Milestone 2 Release #: 0.1 Sprint #: Spring MVC
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 |  | Main Application Module: menu |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Main Application Module: style |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: active registration |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: Database |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database authentication |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: Principle object model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0