## Week1
Project Title: Milestone 8 Release #: 0.7 Sprint #: 8
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a dev I would like my code to be neat and presented in an understandable way. | Code clean up | Everyone | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 3 | As a dev group we would like to present our website. | Presentation (3 Minute video each) | Everyone | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | 3 minutes of explanation of team process and collaboration as well as documentation | 3 minute video of Documentation | Sam | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
|  | 3 minutes of how are backend models work (Post Model, User Model) and how it interacts with the website | 3 minute video of models | Nick | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | 3 minutes of how the blog controller works with the different aspects of the website to pass information and direct users to pages | 3 minute video of blog controller | Casey | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | 3 minutes of how the html/ css interacts with the backend data | 3 minute video of html/ CSS layout | Tim | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
|  | 3 minutes of a walk through of the entire website | 3 minute video of UI design and function | Calista | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | 3 minutes of how we could improve the website and what things we would have liked to implement but couldn't | 3 m inute video for areas of improvement | Adam | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 10 | As a dev I would like to have Sprints, burndown chart, and repo setup for project management. | Design and planning documentation | Tim | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 9 | 7.7143 | 6.4286 | 5.1429 | 3.8571 | 2.5714 | 1.2857 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 9 | 9 | 8 | 8 | 8 | 6 | 0 | 0

## Week2
Project Title: Milestone 2 Release #: 0.1 Sprint #: Spring MVC
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 |  | Main Application Module: menu |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Main Application Module: style |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: active registration |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: Database |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database authentication |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: Principle object model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0